## Sheet1
COSC1076 ¦ Semester 1 2020
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: |  |  | Progress Classes: | Ahead
Group Member: | Faraz Akbari |  |  | On-track
Group Member: | Micheal Trinh |  |  | Behind
Group Member: | Manav Gadhoke |  |  | Way Behind
Tutor:
Class:
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Faraz Akbari | Micheal Trinh | Manav Gadhoke
|  |  | Group Formed | On-track | Weekly Contribution | Behind | Behind | Behind
|  |  | MS Team created | On-track | Issues | I didn't have enough time on that week to start coding.
|  |  | Git Repo created | Behind | Other Notes | -
|  |  | Basic Main menu with "credits" | Behind |  |  |  | Made the main menu the next week when coding had begun.
|  |  | Choice of where to use linked list, vector & array | Behind
|  | Progress | Behind
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Faraz Akbari | Micheal Trinh | Manav Gadhoke
|  |  | Initial Design of ADTs (classes and potential methods) | On-track | Weekly Contribution | I have done the LinkedList Implementation & also created the header file and cpp file for the Factory(ies). | Created header and cpp files for Player and Mosaic classes, and created em list of tiles.
|  |  | Main menu | On-track | Issues | -
|  |  | User Prompt (for gameplay), but no/minimal error checking | Ahead | Other Notes | - |  | Implemented the menu with encapsulated helper functions that are reusable in other parts of the ocde too. Also, error checking already implemented.
|  |  | Linked List implementation | On-track
|  |  | Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required | On-track
|  |  | ADT implementation for storing information, game loop logic not required | On-track
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution
|  |  | Initialisation of data strctures for new game |  | Issues
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic
|  | Progress | Way Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | Fully complete implementation and error free |  | Weekly Contribution
|  |  | Full error checking of user prompt |  | Issues
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes
Final Tests
Group Report Written
|  | Progress | Way Behind